## Fall
GANTT CHART | [24 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | Audomatic Car Movement Detector
[5 empty] | PHASE ONE | [13 empty] | PHASE Two/Three
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2024-06-14 | [6 empty] | 2024-06-21 | [6 empty] | 2024-06-28 | [6 empty] | 2024-07-05 | [6 empty] | 2024-07-12 | [6 empty] | 2024-07-19 | [6 empty] | 2024-07-26
[5 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Project Proposal
Introduction & Background | Emmanuel | 2021-09-27 | 2021-10-04 | 7 | bar: 2024-06-14 M to 2024-06-14 U
Problem Definition | Emmanuel/Jeet | 2021-09-27 | 2021-10-04 | 7 | bar: 2024-06-14 M to 2024-06-14 U
Methods | Ankit/Charles | 2021-09-27 | 2021-10-04 | 7 | bar: 2024-06-14 M to 2024-06-14 U
Potential Results & Discussion | Ankit | 2021-09-27 | 2021-10-04 | 7 | bar: 2024-06-14 M to 2024-06-14 U
Video Recording | Vikranth | 2021-10-04 | 2021-10-07 | 3 | bar: 2024-06-21 M to 2024-06-21 W
GitHub Page | Ankit | 2021-10-04 | 2021-10-07 | 3 | bar: 2024-06-21 M to 2024-06-21 W
Model 1
Data Sourcing and Cleaning | Vikranth | 2021-10-07 | 2021-10-15 | 8 | bar: 2024-06-21 R to 2024-06-28 R
Model Selection | Ankit | 2021-10-15 | 2021-10-18 | 3 | bar: 2024-06-28 F to 2024-06-28 U
Data Pre-Processing | Charles | 2021-10-18 | 2021-10-25 | 7
Model Coding | Jeet | 2021-10-25 | 2021-11-08 | 13 | bar: 2024-07-12 M to 2024-07-19 U
Results Evaluation and Analysis | Emmanuel | 2021-11-08 | 2021-11-16 | 8 | bar: 2024-07-26 M to 2024-07-26 U
Midterm Report | Emmanuel | 2021-11-08 | 2021-11-16 | 8 | bar: 2024-07-26 M to 2024-07-26 U
Model 2
Data Sourcing and Cleaning | Vikranth | 2021-10-18 | 2021-10-22 | 4 | bar: 2024-07-05 M to 2024-07-05 R
Model Selection | Ankit | 2021-10-22 | 2021-10-25 | 3 | bar: 2024-07-05 F to 2024-07-05 U
Data Pre-Processing | Charles | 2021-10-25 | 2021-10-29 | 4 | bar: 2024-07-12 M to 2024-07-12 R
Model Coding | Jeet | 2021-10-25 | 2021-11-19 | 24 | bar: 2024-07-12 F to 2024-07-19 U
Results Evaluation and Analysis | Emmanuel | 2021-11-19 | 2021-11-24 | 5
Model 3
Data Sourcing and Cleaning | Ankit | 2021-10-18 | 2021-10-22 | 4 | bar: 2024-07-05 M to 2024-07-05 R
Model Selection | Ankit | 2021-10-22 | 2021-10-25 | 3 | bar: 2024-07-05 F to 2024-07-05 U
Data Pre-Processing | Ankit | 2021-10-25 | 2021-10-29 | 4 | bar: 2024-07-12 M to 2024-07-12 R
Model Coding | Ankit | 2021-10-25 | 2021-11-19 | 24 | bar: 2024-07-12 F to 2024-07-19 U
Results Evaluation and Analysis | Ankit | 2021-11-19 | 2021-11-24 | 5
Evaluation
Model Comparison | Vikranth | 2021-11-29 | 2021-12-07 | 8
Presentation | All | 2021-11-29 | 2021-12-06 | 7
Recording | All | 2021-12-06 | 2021-12-07 | 1
Final Report | All | 2021-11-29 | 2021-12-07 | 8

## Fall Overview
GANTT CHART | [7 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | NHL Playoff Predictor
[5 empty] | PHASE ONE |  | PHASE TWO | [5 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2024-06-14 | 2024-06-21 | 2024-06-21 |  | 2024-06-28 | 2024-07-05 | 2024-07-12 | 2024-07-19 | 2024-07-26
Project Proposal |  | 2021-09-27 | 2021-10-07 | 10
Introduction & Background | Karishma | 2021-09-27 | 2021-10-04 | 7
Problem Definition | Tim | 2021-09-27 | 2021-10-04 | 7
Methods | Bryan | 2021-09-27 | 2021-10-04 | 7
Potential Results & Discussion | Noah & Gabby | 2021-09-27 | 2021-10-04 | 7
Video Recording | All | 2021-10-04 | 2021-10-07 | 3
GitHub Page | Karishma | 2021-10-04 | 2021-10-07 | 3
Model 1 |  | 2021-10-07 | 2021-11-16 | 39
Data Sourcing and Cleaning | Tim | 2021-10-07 | 2021-10-15 | 8
Model Selection | Karishma | 2021-10-15 | 2021-10-18 | 3
Data Pre-Processing | Tim | 2021-10-18 | 2021-10-25 | 7
Model Coding | Karishma | 2021-10-25 | 2021-11-08 | 13
Results Evaluation and Analysis | Tim | 2021-11-08 | 2021-11-16 | 8
Midterm Report | All | 2021-11-08 | 2021-11-16 | 8
Model 2 |  | 2021-10-18 | 2021-11-24 | 36
Data Sourcing and Cleaning | Gabby | 2021-10-18 | 2021-10-22 | 4
Model Selection | Noah | 2021-10-22 | 2021-10-25 | 3
Data Pre-Processing | Gabby | 2021-10-25 | 2021-10-29 | 4
Model Coding | Noah | 2021-10-25 | 2021-11-19 | 24
Results Evaluation and Analysis | Gabby | 2021-11-19 | 2021-11-24 | 5
Model 3 |  | 2021-10-18 | 2021-11-24 | 36
Data Sourcing and Cleaning | Bryan | 2021-10-18 | 2021-10-22 | 4
Model Selection | Bryan | 2021-10-22 | 2021-10-25 | 3
Data Pre-Processing | Bryan | 2021-10-25 | 2021-10-29 | 4
Model Coding | Bryan | 2021-10-25 | 2021-11-19 | 24
Results Evaluation and Analysis | Bryan | 2021-11-19 | 2021-11-24 | 5
Evaluation |  | 2021-11-24 | 2021-12-07 | 13
Model Comparison | Tim | 2021-11-29 | 2021-12-07 | 8
Presentation | All | 2021-11-29 | 2021-12-06 | 7
Recording | All | 2021-12-06 | 2021-12-07 | 1
Final Report | All | 2021-11-29 | 2021-12-07 | 8
x